## User.Stories
# | As a/an | I want to… | so that I can… | Acceptance Criteria | Notes | Attachment | LOE | Priority | State | Release
1 | CAC/Provider | see an Alert Value on the FAT Pop-Up Notification | I can assess the alert value prior to acting |  | Houston: It may be difficult for the non-numeric tests. PSA tests would be applicable. Imaging / mammogram doesn't make us much sense. Instead of "Alert Value", it should be labeled "Result Value". Quite useful but not critical. Consensus (8/18/14): Table for now |  | High | Medium | Closed
2 | CAC/Provider | scroll through the “Alert Recipient” box | see all the text |  | Houston: This is important. The user needs to see the data. Consensus (8/18/14): Functionality is already in place for next build |  | N/A | High | Closed | RC_1.1
3 | CAC/Provider | have a link to the QI Tool | switch between websites quicker |  | Houston: It's important to be able to move between the two pages quickly. Consensus (8/18/14): Requires customization at each site. Woud require a workaround, maybe enter the URL as a parameter and display it elsewhere |  | High | High | Active
4 | CAC/Provider | be able click a Patient field | access CPRS using the Providers credentials and open the patient record |  | Consensus (8/18/14): Tabled. Would create a situation where the user could now enter CPRS and modify data. Currently, AWARE is read-only with CPRS. |  | N/A | Medium | Closed
5 | CAC/Provider | process “Address Now” pop-ups faster | process more patients |  | Improve CPRS Loading/Performance after clicking the “ADDRESS NOW” button. Houston: Follow usability standards. Priority depends on speed now. If it's slow, then this is the highest priority item thus far. Consensus (8/18/14): May be related to Charleston test environment. Solution could be to use a template (James Vail suggestion). Solution has pros/cons. Waiting for more user testing / different environment testing |  | Low | High | Active
6 | Lab Personnel | know alternate alert recipients (provider/surrogate) | notify critical alerts results immediately |  | Lab personnel wanted to know alternate alert recipients to notify with critical alert results. They were thinking of life and death type tracked alerts like “glucose level”. These they need to immediately notify ordering provider or surrogate by phone within 1 hr. However, they did not want to notify everyone on PSA alerts (which are very common) when a critical value is set. I think Charleston will not want to enable the AWARE PSA tracked alert in the Production account. Houston: Alert is designed now for non-life threatening alerts. This could be something we look to address later. The lab must find another way to do that. It's outside the scope of AWARE. Consensus (8/18/14): Tabled. Outside of AWARE intended scope |  | High | Low / NA | Closed
7 | Provider | know details of a radiology report | have exact analysis before follow-up |  | A physician wanted to know details of radiology report upon AWARE prompt instead of going to details with process alert afterwards before processing “Address now” button in prompt. CACs (from Patrick) had a suggestion in that details of radiology reports could be added to top of the reminder dialog for Abnormal Chest x-ray via Health summary objects embedded into TIU objects place at the top of the reminder dialog to give the physician the exact analysis before doing any subsequent follow-ups. Houston: It's a lot of information to include within a tiny little box. How easy it to get back to the chart? What happens when you decide to close and address later? A hyperlink would be the way to go if possible. Consensus (8/18/14): Workaround is CACs may be able to handle through TIUs |  | (Very) High | High (if hyperlink is possible) / Otherwise Keep open but address | Active
8 | Radiologist/physicians | only see the “Abnormal Chest X-ray” tracked alert to only prompt with serious lung cancer suspicion | to focus alerts towards serious lung cancer |  | 1. Not wanted to prompt for other cases such as Cardiomegaly, etc. The CACs ( thru Peggy) are researching data to use as additional criteria for prompting which are stored in the primary diagnosis in RAD/NUC MED PATIENT file, DIAGNOSTIC CODES and evidence of nodules. -We would have to write logic (i.e. subroutine pointer) to screen for these criteria in addition to just critical alert detection. Houston: AWARE should look for these codes. This is dependent on the code assigned locally. Set it to suspicious for maligancy at the facility. Needs to be decided at facility level. The rules engine must include a "hook" into codes or other criteria. Need to determine if the capability is already there. Consensus (8/18/14): Candidate for later product maturity. CACs might be able to handle through Reminder Dialogs. Consensus (12/1/14): VA will need to build something into its clinical process to register the data, such as "lung nodule". |  | High | High for rules engine hooking into codes defined locally. | Active
9 | Radiologist/physicians | the “Abnormal Mammogram” tracked alert to only prompt with serious breast cancer suspicion | to focus alerts towards serious breast cancer |  | The CACs (thru Peggy) are researching exact Bi-rad codes to screen for as additional criteria for prompting which are stored in the primary diagnosis in RAD/NUC MED PATIENT file, DIAGNOSTIC CODES and Bi-rad codes. We would have to write logic (i.e. subroutine pointer) to screen for these criteria in addition to just critical alert detection. Houston: Same as previous user story. Need to learn degree of standardization of codes for bi-rad or other criteria. Consensus (8/18/14): Same as item #8. |  | High | High for rules engine hooking into codes defined locally. | Active
10 | CAC/Provider | have additional “division” field (from the medical center division file) in the QI reports |  |  | This would fall between institution and service. Houston: This appears to be a local issue. Someone will need to determine what "service" means. Can be very different at every VA. If the level of effort is extremely low, this might be a good addition. Look at current reporting and usage of service-level reporting. Consensus (8/18/14): Maybe something that can be standardized in the future, but not high priority for now. |  | High | Low-Medium | Active
11 | CAC/Provider | have alternate co-signers on specific note titles | have tracked alerts for multiple persons doing follow-ups |  | Not disable nurse providers/case managers who could assist physicians with complete follow-up efforts as team efforts. Don’t exclude non-physician providers from some type of follow-up action(s). Houston: Outside the scope of AWARE. If you want to add a co-signer then that is up to you. Consensus (8/18/14): Functionality is already in CPRS. Out of scope. |  | Medium | NA | Closed
12 | CAC/Provider | have team and surrogate views of a team member or members with need for follow-ups | assist with doing these follow-ups |  | Alert notifications in CPRS to other team members and surrogates works naturally within CPRS. Also, the Alert Cache Viewer allows a pro-active approach to see and assist other team members or surrogated user providers with their alerts. Need study of PCMN teams and surrogates to add proper team logic after team examples are setup in Test account by CACs. Houston: Need clarification on what they have in mind. Agree with comment to "study PCMN team and surrogate practices." The key word is "view". Functionality may already be in place depending on how the account access is configured. Important for the QI tool / Cache Viewer. Facilities need to continue to use surrogate features. Consensus (8/18/14): Monitor for now at Charleston and LB. |  | High | For an individual provider, giving QI access to a team member such Nurse Care manager is important (high). | Active
13 | CAC/Provider | see other provider (ordering provider) when a surrogate or other team member is presented an AWARE prompt | that a primary service provider can see a resulted alert with critical value presented on prompt display, but can leave the follow-up action to the original ordering provider from a specialty service |  | This is especially a useful when an ordering provider is from a specialty service like radiology. Houston: This person wants "Ordering Provider" name listed in the AWARE prompt. Space may be an issue. Consensus (8/18/14): Low priority. Monitor at Charleston and LB for now. |  | High | Low | Active
14 | CAC/Provider | connect associated reminder dialogs for tracked alerts to progress note title | CPRS AWARE redirection to progress note title ( with some “clinic” defined) |  | However, this could be more direct, but is more site specific, and would not lend itself to amore generic AWARE site delivery with allowance of any progress note title and clinic instead of specific named ones. (from James as CAC). Houston: We would like it to, but we didn't see how we could do it. Suggest recommendation of a standardized AWARE note title to be completed with implementation strategies. If you're implementing AWARE, a standard AWARE note title would be important. Blake needs to find out if the progress note content is free text or template generated. Consensus (8/18/14): Related to item #5. Will evaluate more in Production |  | High |  | Active
15 | Provider | connect the Alert Cache Viewer to Tools Menu of CPRS | retrieve all patients needing alert tracking and prompt follow-up action even if not being seen at that time |  | Second login needed presently. May need a generic proxy user login with “provider id’ passed as argument so proxy user that then only shows that CPRS provider’s alerts needing attention. Also, request was made to click intended patient in Alert Cache Viewer to go back into CPRS with that new patient. But since that provider user is still in CPRS, the provider could just directly select that intended patient in CPRS to then address or be prompted for “follow-up needs” on patient closeout. Also a standalone call-up of the Alert Cache Viewer at the same time could provide enough information on patients such that a single one time call-up of CPRS could repetitively allow selection of one or more patients needing follow-up needs”. Houston: Having the single login would be powerful and save time. Consensus (8/18/14): Already resolved. Enhanced by teams being set up (item #12). |  | N/A | Med-High | Active
16 | CAC/Provider | timeout warning in Alert Cache Viewer and KB Editor | avoid timeout issues |  | CSP Pages timeout can be configured in Cache but has no way to send a warning to client browser before the timeout occurs. To implement this, each CSP web page are modified to contain a timer that will warn user 5 minutes before timeout. If user acknowledges the warning dialog, the timer is reset and user is allowed to continue otherwise the URL is expired in the next 5 minutes and user must reconnect. Houston: How long is the time window? This seems like a no-brainer that if you are going to time out, then giving people a warning is nice. The priority is dependent on how often this happens. Consensus (8/18/14): Currently in development and operational. Will be in subsequent build. |  | N/A | High, if common occurrence. | Closed | RC_1.1
17 | CAC/Provider | copy feature in KB editor | speed up reminder dialog creation |  | Adding a “COPY” feature in the KB editor would make it more efficient to make similar Alert type , especially when the same Reminder Dialogs are used as follow-up actions. Replace a Fileman 'Transfer" function. Houston: This makes a lot of sense. Consensus (8/18/14): Currently in development and operational. Will be in subsequent build. |  | N/A | Medium (nice workflow improvement feature) | Closed | RC_1.1
18 | CAC/Provider | new notification type for Amended/Abnormal Imaging in KB editor | create additional/new notifications/reminders |  | Need new Notification Type for Amended/Abnormal Imaging Results: in KB editor’s selection list with new notification type 53. Change in Input Transform in Alert Category’s Notification Type as well. Houston: We don't have the ability to develop new notifications. We're not quite sure what they are asking for. There seems to be a dependency on an alert or notification being in place. Once that exists, AWARE could facilitate this "use case". Consensus (8/18/14): Currently in development and operational. Will be in subsequent build. |  | N/A | TBD or NA. Blake Needs to provide more info. | Closed | RC_1.1
19 | QA Manager | Look-up/Cross reference Alerts on the QI Tool back to CPRS/VistA | To validate that they are valid Alerts and that Follow-Up actions have been taken |  | The AWARE ALERT Cache Viewer only provides 14 days of historical Alert data. The QI Tool stores 180 days of a limited set of Alert data. The limited data does not provide the same details that can be found in the AWARE ALERT Cache Viewer records and what is available in CPRS. The QI Tool only displays the Patient ID. The patient ID field displays the value of the Patient Internal Entry Number (IEN) from the local sites VistA Patient file #2. The Patient ID from the QI Tool cannot easly be used to look-up data in CPRS or AWARE Alert Cache Viewer. Consensus (12/1/14): Being implemented for future build. |  | Medium | High | Closed | RC_1.1.5
20 | QA Manager | Look up alerts for followups for (1) scheduled consult completion, and (2) consult resulting followup made through Alert Cache Viewer/QI tool. | To find out (1) if requested consults are scheduled and scheduled within a week, and (2) whether scheduled consults are actually resulted within a timely period from request. |  | Conversations with Peggy in Charleston regarding these issues as below: Peggy, Here were suggestions to do just that that were made with some research into this with another earlier project. This data was put into the attached document. See end of document on "Team Scheduling Management with Consults" on suggestions with a new type of AWARE alerts for consult tracking of scheduled consult ,or consult resulting completion. George On Tue, Sep 23, 2014 at 3:35 PM, Fralin, Margaret L. <Margaret.Fralin@va.gov> wrote: Thinking ahead – Attached is the alert path for consult requests/orders. We can “time” the actions on the consult, but not the response time to the alert – which has become a big issue. User has 3 options when they get an alert for a new consult (or a comment “approving” a consult): 1.Process them one by one . If they select “process” and then decide not to complete activity (or get called away) – the alert is gone. They would have to have us run a list or use a consult work list. 2.Ignore them – they will remain on the list and the alert number will continue to increase 3.They select “remove” and alert is gone. When you look at the alert screen in CPRS, and a user is scrolling a list of various alerts, “removing” groups, etc. it would be an easy mistake to hit “remove” (in the old VISTA days, you had an option to “ignore”). So – we would need to “track” the consult notifications and be able to see and report on those acted on and those that weren’t. Was alert “deferred” to a later time, and how long did it take to take act Thanks George , that’s it– that’s the second part of it. The first part is tracking how long it takes an approving provider to respond to the consult and approve/disapprove. 12/1/14: Peggy is testing this concept with hemoglobin A1C Consensus (12/1/14): Continue to track and monitor His alert doesn’t re-generate to remind him to act on it – he should get message “you haven’t acted on this alert-do you want to do this now? | Attachments as consult alert examples.doc and Team_Scheduling_Management_with_CONSULTS_072412.doc |  |  | Active
21a | Dr. Robin Onishi (Geriatrics Review) or Lisa LobDell (Case Manager Cancer Imaging Review) - Long Beach | Use Alert Cache Viewer as seen by Recipients including Team recipients | See who has responded and what is left that has no follow-up response(s) made. |  | Dr. Rolland Jenkins will assist Lisa's CPRS Template entry and MS Access use to include equivalent Reminder Dialog responses, and put these items into the AWARE Reminder Dialog to catch analogous activity counting as follow-up action. See also *Team/Recipient Alert below. Also a Team list of 1 was suggested for Lisa that could be defined for a Case Manager to maintain Potential Cancer Imaging Cases that could be seen from the Alert Cache Viewer. However, there could more case managers ( possibly 3) including ones for inpatient following discharges. See also *Team/Recipient Alert below. 1/26/15 consensus: Appears to be a common need from all the clinicians. Wait and see what their thoughts are after prolonged use of application.
21b | Physician Providers/Physician Assistants -Long Beach | Have direct automatic access to Alert Cache Viewer | Avoid High Maintenance of a key assignment with large # of physicians and incoming and leaving residents, interns, etc. |  | Thru Dea # w/o need for VEFA AWARE SINGLE USER security key. . Also automatic review as a single recipient of any AWARE alert from other ordering provider's alerts in a Team. See *Team/Recipient Alert below.
21c | Dr. Vo and Dr. Merchant -Long Beach | Have Team Access as Primary Care Chiefs and Assistant Chief to Review by Any Recipient in Team list |  |  | Review on a multi-recipient, or a multi-team recipient basis ( one provider at a time , not ALL recipients at once). Need the VEFA AWARE ALL KEY to include these functions as well as its use now to review All or individual ordering provider AWARE alerts. Since not assigned to all teams, but need to see all team alerts, and also alerts as a recipient of unassigned patients (i.e. needing a recipient including individually themselves for unassigned patients to them with no Team at all). See *Team/Recipient Alert below.
21d | Nurse Practioners (Samia Holman). and other LVNs, RNs. | Get access to Alert Cache Viewer | Assist with Follow-ups |  | Need VEFA AWARE SINGLE USER key for assistance in follow-up activities with Team call-up for their own provider name ( for comment follow-ups and/or orders with subsequent co-signing need by a physician ). See *Team/Recipient Alert below.
For all of above *Team/Recipient Alert . Need another Selection Box for
a.) Call-up by Single Recipient
b.) Call-up by Single Team Recipient
Additional Selection Box for Specific Team
a.)Pick from PCMN Team List choices
Team could be Physician, LVN,
RN, Extended Provider, maybe
Physician's Assistant
*(continued) Subsequent Provider List in Alert Cache Viewer to select one recipient
a. Recipient List or Specific Team Recipient List
Non-team recipient list could include Attending Provider
( inpatient), ADO, Chiefs who also get forwarded unassigned
patients not on any teams list ( like from ER admissions)
*(continued) Alert Cache Viewer needs a "Team name" column for the listed Alerts, and a "Surrogate" column ( with name of physician who you are acting on behalf of as surrogate). Possible also a "Forwarded From" column for a non assigned patients ( say from the ER) to the Chief of Prime Care Care ( Dr. Vo).
22 | CPRS Users | Have Single Sign-on with Alert Cache Viewer with Tools menu call-up from CPRS ( or at least indefinite log-on after first time) | They have less key strokes |  | An indefinite period of continued logged session can constitute a solution for now. The Vergence and single sign-on may be outside our CSP check, since RPCBroker Session RPC logic not employed. However, a call-up of a stand-alone Alert Cache Viewer may still requires a new separate log-in. 1/26/15 consensus: This occurs first time they log into CPRS (first day or ever?). Harris is looking into this and how it might be implemented.
23 | Dr. Rolland Jenkins | See Alert Tracking IEN with Alert Cache Viewer, and also the pertinent SQL reporting data on left side with QI tool Reports. | Do follow-up analysis to find and verify any follow-up actions |  | We could append IEN to end or start of "ALERT ID" name with a separator for storage in same field of Alert Cache, and subsequent place in a SQL QI Tool table for report purposes. However, after longer durations the purge parameters of certain type alerts in the Alert Tracking file may preclude any look-ups. Also, for the SQL Reports themselves, he prefers to see less useful information switched to the right ( like the "ALERT ID"), and more pertinent information moved to the left so that less "horizontal scrolling" is required to see the pertinent data. Also, our planned Patient lookup w/o any patient Identification info in the SQL table will be useful. 1/26/15 consensus: Re-visit after production use.
24 | Dr. Rolland Jenkins | Use a defined Health Summary object on previous completed follow-up actions per Reminder Dialog elements defined per Alert Type | Use them in a Report under the Reports tab, or at the top of AWARE Reminder Dialogs as TIU objects, for other purposes for Radiology Case manager to display previous historical follow-up activity, and to show Total follow-up activity , etc. |  | Would need to define a Health Summary object for such activity. This could encompass AWARE health factors with a Reminder Dialog including other outside AWARE tracking that have been entered ( like for smoking, etc. ) 1/26/15 consensus: Re-visit after production.
25 | Site Reminder Builder such as Dr. Roland Jenkins or Peggy (Margaret Fralin) | Add local site specific or related AWARE type activities done outside AWARE. | To assist with AWARE follow-up completion. |  | Peggy has modified her reminder dialogs to include elements accounted for in other reminder dialogs outside of AWARE. Dr. Jenkins could also add pertinent items not already into the 2 template related AWARE Reminder dialogs that are being done elsewhere for FOBT and potential CXR Lung Cancer screening including smoking considerations, etc. In order for AWARE to still function, the Reminder Dialog builder has to maintain the Dialog group, Follow-up Comments Group, and General Notes group in teh AWARE Reminder Dialog at those levels, adding any additional elements, and could intermix comment type follow-ups into the Order Group, and orders into the Follow-up Comments Group if needed. 1/26/15 consensus: Re-visit after production.
26 | Physician | Make a follow-up addendum note instead of a new visit note for Reminder dialog data entry. | For many reasons, (1) Keeps the data together in one visit/note combination for later review. (2) Medicare problem with multiple notes, (3) Keep telephone type visit note without patient presence |  | Upon an AWARE prompt "address now" CPRS re-direction to get to a particular Reminder Dialog, would also need a marking of an "historical event" encounter (This could automatically 'clicked" by the CPRS/AWARE program ( modified CPRS 30a AWARE program), or done manually by physician). Physician could override a prepared "new visit" selection directed now in CPRS/AWARE program ( modified CPRS 30A program) by choosing an older visit date/time ( appointment/inpatient admission) last seen for "ordered test". This date/time visit of an associated ordering a test would then be the time to search ahead to see if any follow-up activity has been done ( instead of from a later date/time from the actual resulting ALERT date/time). Change would be required in Mumps code for Alert Cache Viewer and Mumps code for deciding any Alert prompting action in CPRS that is made in the Aware DLL. (there is pointer information is available in an ALERT to trace back to its associated "ORDER" file entry date/time). 1/26/15 consensus: Re-visit after production.
27 | Chiefs of Services including Dr. Wong ( Chief of Informatics), and Dr. Tanavoli | Know many times an AWARE prompt is skipped ( "address later") per provider concatenated with last date time of "address later" in Alert Cache. | Review work of staff, and see what is done over vacations, etc. that don't get follow-up. |  | Changes in CPRS/AWARE and/or DLL to pass data to identify Alert ID, and increment count and last "address later" date into an Alert Cache entry. 1/26/15 consensus: Makes a lot of sense to implement. Re-visit after production.
28 | Provider | See most critical alerts in a top of current notification window upon patient selection , or new panel above color coded to stand out. | I can identify most critical patients with outstanding alerts to do follow-up on. |  | Idea shared with George Welch before. However, possible problems with 508 compliance as well. Separate panel above w/o color may be ok too. Some exceptions to color coded data can be allowed as the entries would still be in regular notification window. 1/26/15 consensus: Looking for 'at a glance' capability. Re-visit after production.
29 | Long Beach Physician | To forward my whole personal patient list to another provider | Pass work for various reasons. |  | CPRS allows surrogates now for alerts with some of theses patients. CPRS would have to do this personal list transfer. 1/26/15 consensus: Powerful item. Could be outside of AWARE and a CPRS function. Re-visit after production.
30 | Dr. Chambers | Use the "TUMOR Code 1" alert category defined for Long Beach Radiology. | Use this as Filtering on Abnormal Images |  | We have not identified the Radiology ADPACK on how this was done. There is also a "Code 1" alert category, as well as a supposedly national standard "Abnormal imaging Reslt: Needs Attn:" with "Atn" replacing "Attn" at Long Beach ( ?). Also needs notice for 48 hrs instead of 7 days follow-up completed. Dr. Chambers has said that for now Long Beach VA does not need additional filtering logic as proposed in line item 8 above including details in attachment in line item 8 that the Charleston VA could need for their use. 1/26/15 consensus: Some of this functionality is available now. "Notice for 48 hrs instead of 7 days" can be a separate user story.
31 | Dr. Da Costa (Chief of Lab) and thru Dr. Jenkins | Identify the Lab Alert Id for FOBT | Have proper AWARE FOBT alert tracking |  | Alert lab test and corresponding alert type name identified. Usually the same, but not here. The lab test name is "FOBT1 IMMUNOASSAY". Alert type name is [OCCULT BLOOD - IMMUNOASSAY]. Need to use extended method in Vista Install Guide to generate these type alerts as alert type name not same as lab test name, and no site/specimen is provided. Production account data name identified by Dr. Jenkins. Lab tech needs to call primary care physician within 1hr on critical lab alert, and 24hrs on abnormal biopsy. We made suggestion to always assign a surrogate to residents before they leave service. 1/26/15 consensus: Re-visit after production.
32 | Nancy Horvath & Sue Fawson- Long Beach CACs, along with Jeannine Lestina | Have specific instructions on configuring the basic site specific alert categories and alert types for AWARE derived from the basic ones delivered with AWARE in a first time setup of AWARE. | To more easily configure a 1st time AWARE setup for the basic Alert types. |  | 5 basic reviews and preparation in a sequence for them to use as a Guide (1.) Determine Radiology Alert Category(s) and Alert type(s) name considerations from Radiology Dept., (2.) Next determine Laboratory test names for Alert type from Laboratory Dept., (3.) Next have a Clinical Informatics Champion sort out exact needs with Alert Categories and Alert type names from sections (1.) and (2.), and (4.) Have a Clinical Informatics person provide the CACs with the exact data names, and then (5. ) The CACs enter this data into the KB Editor using some distinct entry instructions provided in the Vista Install document, or attachment. 1/26/15 consensus: This is the CAC cheat sheet. On our weekly task list. Not really a development user story.
33 | Dr. Chambers | Use AWARE with imaging results | For catching all cancers | Approval by Dr. Jenkins, Dr. Chambers and CACs | "Code 1 TUMOR Abnormal Imaging Results:" alert category , he would like to use any imaging procedure to catch all types of cancers. The follow-ups in Reminder dialogs we have considered are depending on each type of cancer detected and its stage. Also, our task was for Lung Cancer ( i.e. typically Chest x-ray). We also have a "GENERIC" name field for noting the kind of cancer (i.e. "Lung Cancer") in each Alert Type name. For imaging alert type names these are related to the Rad/Nuc Med Procedure names. Procedures with a common follow-up treatment (via Reminder dialog) could all have the same "GENERIC" name. We could start with some multiple imaging tests regarding the earlier detection of such cancer with some Chest and Thoracic imaging results. Dr. Jenkins also had suggested some of these basic alert image types. Chest imaging results could be from the following AWARE alert types: "CHEST 2 VIEW", "CHEST OBLIQU", "CHEST SINGLE", "CHEST SPECIA", "CHEST ECHO ", "CHEST W/O M". Thoracic imaging results could be from the following AWARE alert types: "CT THORAX W/", "CT THORAX W&", "CT THORACIC S", "MRI CERVICAL", "MRI THORA-LU", "MRI THORACO-", "MRI THORACOL", "MYELOGRAM TH", "AORTOGRAM TH", "CTA, ARTERIA". 2/2/15: Configuration for production can be communicated through cheat sheets.
34 | Nancy Horvath & Sue Fawson- Long Beach CACs | Consider AWARE dll prompting with Patient Selection as well as Patient Closeout as a suggestion. | So more versatility could result |  | Checkout be made to see if this would work. It probably will not as it is now. It also may be that the Patient Closeout entry is too specific fro AWARE. May need to make it more generic for any other COM object using a Patient Closeout entry in CPRS. 2/2/15: Run by first users for confirmation. Risk is this feature could be more intrusive.
35 | Dr. Wong - Long Beach | Make changes in Alert field names in QI Tool Reports | See meaningful names |  | FAT , call it something else (DR. Wong), also NONACK not meaningful in QI reports 2/2/15: Will be resolved in next build.
36 | Informatics Physician | Define AWARE Alert types | To show them with their original full & non abbreviated name |  | Names now are limited in number of characters depending on total Alert Category name and Alert type length(s). Could have an improvement by tracing the RADI NUC/MED PROCEDURE name to allow full entries of Alert category and Alert type name in KB Editor. Also allow full AWARE DLL prompt name to appear. Change in Alert Cache Builder and AWARE dll logic. Also noted from AWARE developers ( i.e. G. Welch). 2/2/15: Run by first users for confirmation. Dr. Jenkins and George are sources.
37 | Informatics Physician | Allow multiple similar imaging procedure names used as Alert type names to be grouped together. | For better information management purposes |  | Could have a multiple of additional imaging procedure names beyond a basic one for an Alert type ( i.e.. CHEST 2 VIEWS as the primary one ) with secondary or additional image procedures such as other Chest or Thoracic images procedures that could be defined in another multiple field(s) in the KB editor, but which would all be under just one Alert type entry. This would allow for fewer, and more manageable AWARE alert types. Also noted from AWARE developers (i.e. G. Welch). 2/2/15: Future enhancement
38 | Clinician/Provider | I want to see Critical Alerts pop-up when I open a patients chart in CPRS. | So I can plan follow-up actions before the patient completes the vist. |  | If the AWARE Alert Prompt is displayed on chart open and chart close, the follow uo success rate will increase. Patient may have left the office when the provider closes the chart. 2/2/15: Same as #34.
39 | Provider, QA Manager | I want the Alert Cache Veiw defualt sort to be Date, then Patient Name | Make data prestentation more meaningful. |  | Alert data would be displayed as the providers normaly see information 2/2/15: Will be in next build. |  |  |  | Completed
40 | Provider, QA Manager | I want the Alert Cache Veiw to be able to export/save the data to CSV or Excel formats | Alert data can be grouped as needed by the users. |  | Provides greater functionality. 2/2/15: Future enhancement.
41 | Provider, QA Manager | I want the Alert Cache Veiw to be able to filter by the Follow-Up column | So I can quickly see only patients with no follow-ups. |  | Provides greater functionality. 2/2/15: Future enhancement. |  |  |  | Completed
42 | Provider, QA Manager | I want the Alert Cache Veiw to be able to filter by the Alert Category column | So I can quickly see patients by Alert Category. |  | Provides greater functionality. 2/2/15: Future enhancement.
43 | Provider, QA Manager | I want the Alert Cache Veiw to be able to filter by the Alert Type column | So I can quickly see patients by Alert Type. |  | Provides greater functionality. 2/2/15: Future enhancement.
44 | Provider, QA Manager | I want the Alert Cache Veiw to be able to have a search filter | So I filter by other criteria |  | Provides greater functionality. 2/2/15: Future enhancement.
45 | Provider, QA Manager | I do not want to re-enter my Access and Verify codes when the Alert Cache Viewer is opened from CPRS Tools. | So I can save time. |  | Provides greater functionality. 2/2/15: Currently being researched. Can be added to training materials. |  |  |  | Completed
46 | Provider, QA Manager | I want the Abbrevation "FAT" changed to "Tracking" |  |  | Provides greater functionality. 2/2/15: Will be in next build. |  |  |  | Completed
47 | Provider, QA Manager | I want the QI Tool to provide a report of the Providers that were Alerted. | To improve the validation and tracking of patient follow-up's. |  | Provides greater functionality. 2/2/15: Future enhancement. Shows everyone who was notified of an alert (recipients). Could also be a component of the Alert Cache Viewer.
47 | Provider, QA Manager | I want the QI Tool to provide a report by Percentage. | To improve the validation and tracking of patient follow-up's. |  | Report would provide percent with No Follow by Facility, Alert Type, Alert Category, etc. Report would provide percent with Follow by Facility, Alert Type, Alert Category, etc. 2/2/15: Future enhancement.
48 | Provider, QA Manager | I want the AWARE Alert Viewer to consistently display the Patient ID Fields as the first initial of the Patients Last Name and the Last four digits of the SSN. | To improve the validation and tracking of patient follow-up's. |  | Change the AWARE Alert Viewer Status Tab so the Patient ID field is changed from the DFN to U1$N. |  |  |  | Active
49 | Provider, QA Manager | I want the AWARE Alert Viewer to recognize specific CPRS Progress Notes as valid AWARE Follow-Up Actions. | To improve the validation and tracking of patient follow-up's. |  | Modify the AWARE KB Editor Alert Types so the a CPRS Progress Note can be configured as valid Follow-Up. |  |  |  | Active
Note on H1: Andrew Q Smith: Low <2hrs Med 2-5hrs High >5hrs
Note on J1: Sort by: Active Closed